## Tracker
PROJECT SCHEDULE & SPRINT BACKLOG
Task ID | Chapter/Sprint | Task / User Story | Owner | Start Date | Due Date | Priority | Status | % Complete | Evidence / Deliverable
T01 | Sprint 0: Proposal (2-8 Oct) | Write the problem project proposal and obtain topic acceptance | Gedion Basson | 2026-10-02 | 2026-10-07 | High | Complete | 100% | Project Proposal folder; Topic_Acceptance_Group3.pdf; commits 08ea06b, e03757d
T02 | Sprint 0: Proposal (2-8 Oct) | Revise the proposal after supervisor comments (scope narrowed to three core features) | Moegammad Green, Gedion Basson | 2026-10-07 | 2026-10-07 | High | Complete | 100% | SPM Problem Project Proposal (Revised).md; commits 5465df5, 78eef1e
T03 | Sprint 0: Proposal (2-8 Oct) | Create the GitHub repository, folder structure and add collaborators | Moegammad Green, Gedion Basson | 2026-10-07 | 2026-10-08 | High | Complete | 100% | github.com/Noobey32/TrackWIL; commits 629b191, cb29667, 725798c
T04 | Sprint 0: Proposal (2-8 Oct) | Group declaration and roles; ethical clearance confirmation (folder 00) | Gedion Basson | 2026-10-08 | 2026-10-08 | High | Complete | 100% | 00_Project_Administration; commit 08aaa44
T05 | Sprint 0: Proposal (2-8 Oct) | Project charter and work plan (version 1) | Moegammad Green | 2026-10-08 | 2026-10-09 | High | Complete | 100% | 09_Project_Management_Evidence/Project_Charter_and_Work_Plan; commits 9134c50, 4ebeae7
T06 | Sprint 1 / Week 2 (9 Oct) | Chapter 1: Introduction (draft) | Sihle Kayise | 2026-10-07 | 2026-10-09 | High | Complete | 100% | 01_Introduction; commit 800fe83
T07 | Sprint 1 / Week 2 (9 Oct) | Chapter 2: Literature Review and Literature Review Matrix | Dylan Shepard | 2026-10-08 | 2026-10-09 | High | Complete | 100% | 02_Literature_Review; commits 12de6ad, 16f0efc
T08 | Sprint 1 / Week 2 (9 Oct) | Harvard reference list | Dylan Shepard | 2026-10-09 | 2026-10-09 | Medium | Complete | 100% | Week 2 Submission/Reference list; commit 79cf0f8
T09 | Sprint 1 / Week 2 (9 Oct) | Compile and submit Week 2 submission (Group3_Week 2.pdf) | Gedion Basson | 2026-10-09 | 2026-10-09 | High | Complete | 100% | Week 2 Submission folder; commits 87c899a, 5a84b15
T10 | Sprint 1: App (9-15 Oct) | US-01 Next.js project set-up, sign-in, sign-out and sessions | Moegammad Green | 2026-10-12 | 2026-10-12 | High | Complete | 100% | 05_Source_Code/trackwil; commits 32c3f87, 5893fee
T11 | Sprint 1: App (9-15 Oct) | US-02/US-03 Logbook entries with evidence upload and hour progress | Moegammad Green | 2026-10-12 | 2026-10-12 | High | Complete | 100% | src/app/student, actions/logbook.ts; commit 5893fee
T12 | Sprint 1: App (9-15 Oct) | US-04/US-05 Submit for verification and mentor approval through a one-time link | Moegammad Green | 2026-10-12 | 2026-10-12 | High | Complete | 100% | src/app/verify, actions/verify.ts; commits 5893fee, 369fe55
T13 | Sprint 1: App (9-15 Oct) | US-07 Coordinator dashboard (On track, Awaiting verification, Overdue) | Moegammad Green | 2026-10-12 | 2026-10-12 | High | Complete | 100% | src/app/coordinator, lib/logbook-metrics.ts; commit 5893fee
T14 | Sprint 1: App (9-15 Oct) | US-01 Student sign-up with CTU email and password rules | Moegammad Green | 2026-10-12 | 2026-10-12 | Medium | Complete | 100% | lib/signup-validation.ts; commit 5883791
T15 | Sprint 2 / Week 3 (16 Oct) | UML, ERD and architecture diagrams (draw.io) | Moegammad Green | 2026-10-14 | 2026-10-14 | High | Complete | 100% | 04_System_Design_and_Development/diagrams; commit 29c2cab
T16 | Sprint 2 / Week 3 (16 Oct) | Chapter 4 draft (sections 4.1 to 4.6) | Moegammad Green | 2026-10-14 | 2026-10-15 | High | Complete | 100% | Chapter_4_System_Design_and_Development.docx; commit ad457c0
T17 | Sprint 2 / Week 3 (16 Oct) | Software Requirements Specification (SRS) | Gedion Basson | 2026-10-14 | 2026-10-14 | High | Complete | 100% | 03_Requirements_and_Methodology; commit f84afa3; PR #2
T18 | Sprint 2 / Week 3 (16 Oct) | Chapter 3: Requirements and Methodology (draft and formatting) | Sihle Kayise, Dylan Shepard | 2026-10-14 | 2026-10-15 | High | Complete | 100% | commits daf3c24, 52d753c
T19 | Sprint 2 / Week 3 (16 Oct) | Revise Chapters 1 and 2 using Week 2 feedback; revision table | Dylan Shepard | 2026-10-15 | 2026-10-15 | High | Complete | 100% | commits c5794a4, b4c0d76, f255d6e, 917f34f
T20 | Sprint 2 / Week 3 (16 Oct) | Compile and submit Week 3 submission with work plan and progress report | Gedion Basson, Moegammad Green | 2026-10-15 | 2026-10-15 | High | Complete | 100% | Week 3 Submission folder; commits 98e8363, 6b6b05b; PR #3
T21 | Sprint 3 / Week 4 (23 Oct) | Chapter 5 draft, Test Plan and first test cases | Sihle Kayise | 2026-10-20 | 2026-10-22 | High | Complete | 100% | 06_Testing_Results_and_Evaluation; commit 48df206; PR #4
T22 | Sprint 3 / Week 4 (23 Oct) | Replace JSON file storage with an SQLite database (schema, seed, transactions) | Gedion Basson | 2026-10-22 | 2026-10-22 | High | Complete | 100% | 05_Source_Code/trackwil/database; commit 7080e7f; PR #5
T23 | Sprint 3 / Week 4 (23 Oct) | Update Chapters 1-4, SRS and Database Design to match the build; class and activity diagrams; UI screenshots | Gedion Basson | 2026-10-22 | 2026-10-23 | High | Complete | 100% | commit 2634d57; PR #6
T24 | Sprint 3 / Week 4 (23 Oct) | Update sprint backlog, risk register and weekly progress report | Gedion Basson | 2026-10-23 | 2026-10-23 | Medium | Complete | 100% | 09_Project_Management_Evidence (this branch)
T25 | Sprint 3 / Week 4 (23 Oct) | Fix defect: unsigned session cookie allows impersonation; retest | Gedion Basson | 2026-10-23 | 2026-10-25 | High | Not Started | 0% | Issue I02 in Risk Register; Defect Log
T26 | Sprint 3 / Week 4 (23 Oct) | Execute all test cases with actual results; complete Defect Log and Requirements Traceability Matrix | Dylan Shepard, Sihle Kayise | 2026-10-23 | 2026-10-26 | High | In Progress | 20% | 06_Testing_Results_and_Evaluation workbooks
T27 | Sprint 3 / Week 4 (23 Oct) | Record the 3-5 minute screen-recorded walkthrough | Gedion Basson | 2026-10-23 | 2026-10-23 | High | Not Started | 0% | Video link on first page of Group3_Week4.pdf
T28 | Sprint 3 / Week 4 (23 Oct) | Compile and submit Week 4 submission (Group3_Week4.pdf) | Gedion Basson | 2026-10-23 | 2026-10-23 | High | In Progress | 50% | Week 4 Submission folder
T29 | Sprint 4: Final (24-29 Oct) | Fix defect: entry stays Pending when its link expires; retest | Moegammad Green | 2026-10-24 | 2026-10-26 | Medium | Not Started | 0% | Issue I03 in Risk Register; Defect Log
T30 | Sprint 4: Final (24-29 Oct) | Upgrade Next.js to a patched version and rerun tests | Moegammad Green | 2026-10-24 | 2026-10-27 | Medium | Not Started | 0% | Issue I04 in Risk Register
T31 | Sprint 4: Final (24-29 Oct) | Usability test and questionnaire (only with written permission and consent) | Dylan Shepard | 2026-10-26 | 2026-10-27 | Medium | Blocked | 0% | Awaiting written campus permission (Ethical Clearance Confirmation)
T32 | Sprint 4: Final (24-29 Oct) | Chapter 5: Testing, Results and Evaluation (final) | Sihle Kayise, Dylan Shepard | 2026-10-24 | 2026-10-28 | High | In Progress | 30% | Chapter_5_Testing_Results_and_Evaluation.docx
T33 | Sprint 4: Final (24-29 Oct) | Chapter 6: Conclusion and Recommendations | Gedion Basson | 2026-10-26 | 2026-10-28 | High | Not Started | 0% | 07_Conclusion_and_Recommendations
T34 | Sprint 4: Final (24-29 Oct) | Final dissertation: front matter, abstract, contents, lists, references and appendices | Gedion Basson | 2026-10-26 | 2026-10-28 | High | Not Started | 0% | 08_Final_Dissertation
T35 | Sprint 4: Final (24-29 Oct) | Complete the two incomplete Chapter 2 references | Dylan Shepard | 2026-10-24 | 2026-10-26 | Medium | Not Started | 0% | Chapter 2 reference list
T36 | Sprint 4: Final (24-29 Oct) | Presentation slides and demo script with backup plan | Moegammad Green, All | 2026-10-24 | 2026-10-28 | High | Not Started | 0% | 11_Presentation_and_Demonstration
T37 | Sprint 4: Final (24-29 Oct) | Individual Contribution Forms with Git evidence references | All members | 2026-10-24 | 2026-10-28 | High | Not Started | 0% | 12_Assessment/Individual_Contribution_Form.docx
T38 | Sprint 4: Final (24-29 Oct) | Turnitin similarity check (below 15%) and final submission checklist | Gedion Basson | 2026-10-28 | 2026-10-29 | High | Not Started | 0% | 12_Assessment/Final_Submission_Checklist.xlsx
T39 | Sprint 4: Final (24-29 Oct) | Rehearse the presentation and live demonstration in business attire | All members | 2026-10-28 | 2026-10-29 | High | Not Started | 0% | Demo Script