## Tracker
DEFECT / BUG LOG
Defect ID | Date | Feature | Description | Severity | Priority | Reported By | Assigned To | Status | Fix / Resolution | Retest Result | Evidence
DEF-01 | 2026-10-22 | Sign-in / sessions | The session cookie stored the user id without a signature. Setting the cookie to "coordinator-1" in a browser opened the coordinator dashboard without a password. Reproduced on build 7080e7f: HTTP 200 and the dashboard was shown. | Critical | High | Gedion Basson | Gedion Basson | Closed | The cookie is now <userId>.<HMAC-SHA256 signature> and is checked in constant time; the secret comes from TRACKWIL_SESSION_SECRET or is generated once into data/session-secret. Commit 5268c2e. | Pass: TC-121 (forged and tampered cookies rejected); TC-110 to TC-119 still pass | evidence/system_test_run_2026-10-23.txt
DEF-02 | 2026-10-22 | Verification links | If a mentor link expired before the mentor responded, the entry stayed Pending verification with no Submit button, and the server refused to resubmit it ("Only draft or rejected entries can be submitted."). Reproduced on build 7080e7f. | Medium | Medium | Gedion Basson | Gedion Basson | Closed | A pending entry with no active link can be submitted again for a new link; the entry page shows an expiry notice and the Submit button. Commit 5268c2e. | Pass: TC-137; TC-129 confirms an entry with an active link still cannot be resubmitted | evidence/system_test_run_2026-10-23.txt
DEF-03 | 2026-10-23 | Responsive layout | On a 375 px phone screen the logbook and dashboard tables made the page 580 px wide and cut off the right-hand columns with no way to scroll. | Medium | Medium | Gedion Basson | Gedion Basson | Closed | The page container is now full width and each table scrolls inside its own box (overflow-x-auto). Commit 5268c2e. | Pass: TC-145 (page width 375 px in Chrome 155 and Edge 155) | evidence/mobile_375px_chrome; evidence/mobile_375px_edge
DEF-04 | 2026-10-22 | Dependencies | The production build reports that Next.js 16.4.0 is affected by a known security vulnerability. | High | Medium | Gedion Basson | Moegammad Green | Open | Upgrade Next.js on a separate branch, rebuild and rerun npm run test:system before merging. | Not yet retested | npm run build output
DEF-05 | 2026-10-23 | Sign-in page | The demo accounts box on the sign-in page lists the student and coordinator accounts but not the lecturer account. | Low | Low | Gedion Basson | Moegammad Green | Open | Add lecturer@ctucareer.co.za / lecturer123 to the demo accounts box. | Not yet retested | screenshots/01_login.png