## Tracker
PROJECT RISK, ISSUE & CHANGE REGISTER
ID | Type | Date | Description | Likelihood | Impact | Priority | Owner | Mitigation / Action | Status | Due Date | Outcome
R01 | Risk | 2026-10-08 | Written campus permission to collect staff or student data arrives late or is refused, so no real usability or time-on-task data can be collected. | Medium | Medium | Medium | Gedion Basson | Develop, test and demonstrate with synthetic data only; state this in the dissertation; keep the questionnaire ready to run within a day if permission arrives. | Open | 2026-10-27
R02 | Risk | 2026-10-08 | Scope creep: analytics, bulk exports or audit logs are started before the three core features work. | Medium | High | High | Gedion Basson | Stretch goals only after the core works; deferred requirements recorded in Chapter 3. | Closed | 2026-10-22 | Core features delivered; stretch goals deferred to future work.
R03 | Risk | 2026-10-08 | A Friday milestone slips because members also have other assessments. | High | High | High | Gedion Basson | Owner tells the group lead in the same week; cut back to the core features; daily plan in the weekly progress report. | In Progress | 2026-10-29 | Week 2 and Week 3 submitted on time.
R04 | Risk | 2026-10-09 | Uneven Git contributions between members reduce individual marks (rubric criteria 6 and 10). | Medium | High | High | Gedion Basson | Each member commits their own work on a name/task branch and merges through a pull request; contribution forms reference specific commits. | Open | 2026-10-28
R05 | Risk | 2026-10-12 | JSON file storage rewrites the whole file on each change and has no keys or constraints, so data could be corrupted or become inconsistent. | Medium | High | High | Moegammad Green | Replace with an SQLite database with foreign keys, CHECK constraints and transactions. | Resolved | 2026-10-22 | Migrated to SQLite (PR #5, commit 7080e7f).
R06 | Risk | 2026-10-12 | Harmful or unexpected files uploaded as evidence. | Low | High | Medium | Moegammad Green | Allow only PDF and image types, store under random names outside the public folder, serve only to the owner and staff. | Resolved | 2026-10-12 | Implemented in actions/logbook.ts and api/evidence route.
R07 | Risk | 2026-10-23 | The live demonstration fails (laptop, network or data problem). | Medium | High | High | Moegammad Green | Run locally with the SQLite seed data; npm run db:reset before the demo; screen-recorded walkthrough and screenshots as backup; second laptop ready. | Open | 2026-10-29
R08 | Risk | 2026-10-23 | Turnitin similarity of 15% or more. | Low | High | Medium | Dylan Shepard | Write in own words, cite every source in Harvard style, check the full draft early. | Open | 2026-10-28
I01 | Issue | 2026-10-22 | Chapters 1 and 3 and the SRS described mentor accounts, a separate lecturer dashboard and PostgreSQL, which do not match the system that was built. | High | Medium | High | Gedion Basson | Rewrite the documents to match the build and record deferred requirements. | Resolved | 2026-10-23 | Documents updated (PR #6).
I02 | Issue | 2026-10-22 | Security defect: the session cookie stores the user id without a signature, so a user who edits the cookie can impersonate another account. | High | High | High | Gedion Basson | Sign the session cookie or use a random session token stored in the database; add a test case and retest. | Resolved | 2026-10-25 | Fixed on 23 Oct 2026: signed session cookie (commit 5268c2e); DEF-01 closed after retest TC-121.
I03 | Issue | 2026-10-22 | Defect: when a mentor link expires before the mentor responds, the entry stays Pending verification and the student cannot resubmit it. | Medium | Medium | Medium | Gedion Basson | Allow resubmission of a pending entry that has no active link; add a test case and retest. | Resolved | 2026-10-26 | Fixed on 23 Oct 2026 (commit 5268c2e); DEF-02 closed after retest TC-137.
I04 | Issue | 2026-10-22 | The Next.js build reports that version 16.4.0 is affected by a known security vulnerability. | High | Medium | Medium | Moegammad Green | Upgrade Next.js on a separate branch and rerun all tests before merging. | Open | 2026-10-27
I05 | Issue | 2026-10-23 | Two Chapter 2 references are incomplete (Hains-Wesson et al. 2026; Sonia Online n.d.). | High | Medium | Medium | Dylan Shepard | Find the original sources and complete the Harvard references. | Open | 2026-10-26
I06 | Issue | 2026-10-23 | Workplace mentors cannot open evidence files from the verification link, because evidence downloads require sign-in. | High | Medium | Medium | Moegammad Green | Recorded as a limitation and future work; mentors verify from the entry description. | Accepted | 2026-10-23 | Documented in Chapter 3 (deferred requirements).
C01 | Change | 2026-10-07 | Scope narrowed to three core features (logbook, token verification, coordinator dashboard) after supervisor feedback; analytics, exports and audit logs moved to stretch goals. | Low | Medium | Medium | Gedion Basson | Revise the proposal and work plan. | Closed | 2026-10-07 | Revised proposal accepted (commit 5465df5).
C02 | Change | 2026-10-07 | Week 1-7 plan replaced with one-week sprints ending on each Friday submission, finishing on 29 October. | Low | Medium | Medium | Gedion Basson | Update the methodology and work plan. | Closed | 2026-10-07 | Sprint plan in Chapter 3.
C03 | Change | 2026-10-12 | Workplace mentors verify through a one-time link instead of having accounts and a mentor dashboard. | Low | Medium | Medium | Moegammad Green | Implement token verification; update requirements and design. | Closed | 2026-10-23 | Implemented; Chapters 1, 3 and 4 updated.
C04 | Change | 2026-10-12 | Lecturers use the coordinator dashboard instead of a separate lecturer dashboard. | Low | Low | Low | Moegammad Green | Route lecturers to /coordinator; update requirements. | Closed | 2026-10-23 | Implemented; lecturer demo account added.
C05 | Change | 2026-10-22 | Data storage changed from JSON files to SQLite. | Low | High | Medium | Gedion Basson | Migrate the repository layer only; rerun all tests. | Closed | 2026-10-22 | PR #5; 28 automated checks passed.
C06 | Change | 2026-10-22 | Written mentor feedback on rejected entries deferred to future work. | Low | Medium | Medium | Gedion Basson | Record in the deferred requirements and Chapter 6 recommendations. | Accepted | 2026-10-23 | Documented in Chapter 3.